## Slide 1: Satellite Integration Report
Date

## Slide 2: Satellite Status report – Week of 2016-11-01 Reason for status: Major satellites on track, Issues being solved in Unit Test
Rating:
 Fully on track, no intervention needed
 Off-track, but a credible plan is in-place to get back on-track
 Off-track and no credible plan in-place to get back on-track. Intervention required.
 Completed.
Logistic Delivery Satellites – Unit Test (end-to-end) in progress
Dynasys UT closed
TMs Kewilll UT closed
Activities completed
Intervention or decision required | Raised by Interface | Responsible | Due by
Confirm Nutrade WeMap changes Feedback
Close Nutrade flat file ECC design
Close Nutrade GD design
Finalize GKO fixes
Evaluate decommissioning of AILOG
Activities for coming week
Data Objects Needed |  |  | 
COMM | PnS | FIP | Nut
Customer | Transport master data | Credit Limit | Transaction data
Material | Transaction data | Bank Data | Customer
Pricing | Carrier tracking data | Fiscally relevant transactional data | Material
Transaction data | Freight invoices | FI/CO-postings | 
 | Production orders |  | 

## Slide 3
Satellites | Data needed | Streams | Solution Readiness (RAG) | Environment Readiness (RAG) |  |  | Data Requirements identified (RAG) | Cutover Strategy (RAG)
 |  |  |  | IST | UAT | PROD |  | 
Agroview | NO (stand alone**) | COMM | G (stand alone) | N/A |  |  | N/A | R (Unknown)
PecSyn | YES | COMM | A (still in design phase) | A |  |  | A (MD/TD) | R (Unknown)
Plussoft SaaS | YES (MD) | COMM | R (SCA approval pending) | R |  |  | G (MD) | R (Unknown)
SPOT | YES (MD/TD) | COMM | R (stand alone - design on going) | A |  |  | A (MD/TD) | R (Unknown)
Teamspace (SIPExc mngt) | NO (stand alone**) | COMM | R (stand alone - design on going) | A |  |  | N/A | R (Unknown)
Bank Payment Processing | YES (TD) | FIP |  |  |  |  |  | 
Credito Rural | YES (MD/TD) | FIP | G (flat file ready) | G |  |  | G (MD/TD) | R (Unknown)
Easy IRPJ | YES (MD/TD) | FIP | G (flat file ready) | G |  |  | G (MD/TD) | R (Unknown)
HR | YES (MD) | FIP | G (interfaces ready) | G |  |  | G (MD) | R (Unknown)
MasterSAF DW | YES (MD/TD) | FIP | G (interfaces ready) | G |  |  | G (MD/TD) | G (MD full upload/refresh)
Payroll | ? | FIP |  |  |  |  |  | 
Rhadar Cartão de Visitar | YES (MD) | FIP | G (flat file ready) | G |  |  | G (MD) | R (Unknown)
Serasa | NO* | FIP | A (interface build in progress) | A |  |  | G (TD) | N/A
Synseg | YES (MD) | FIP | G (flat file ready) | G |  |  | G (MD) | R (Unknown)
TPS (Pricing) | YES (MD/TD) | FIP | A (flat file build in progress) | G |  |  | G (MD/TD) | R (Unknown)
TP-Tool / BW | YES (MD/TD) | FIP | A (interface build in progress) | A |  |  | G (MD/TD) | R (Unknown)
GD Nutrade | YES (MD/TD) | NuTrade | A (flat file in design) | A |  |  | A (in design) | R (Unknown)
ML Substitute | NO (stand alone**) | NuTrade | R (build plan unknown) | R |  |  | R (Unknown) | R (Unknown)
Monitoramento Logistico | NO (decomission) | NuTrade | N/A | N/A |  |  | N/A | N/A
WebMap | YES (MD/TD) | NuTrade | A (flat file build in progress) | A |  |  | G (MD/TD) | G (MD delta update)
Ailog | NO (on hold) | PnS | N/A | N/A |  |  | N/A | N/A
Carrier Web Services | NO* | PnS | A (interface in unit test) | G |  |  | G (TD) | N/A
Dynasys | YES (MD/TD) | PnS | A (flat file ready) | G |  |  | G (MD/TD) | G (MD manual maint)
GKO Frete | YES (MD/TD) | PnS | A (interface in unit test) | A |  |  | G (MD/TD) | G (MD delta upload)
One Source Global Trade | YES (MD/TD) | PnS | A (interface build in progress) | A |  |  | G (MD/TD) | R (Unknown)
Painel e-Kanban | NO (decomission) | PnS | N/A | N/A |  |  | N/A | N/A
TMS Kewill | YES (MD/TD) | PnS | A (interface ready) | G |  |  | G (MD/TD) | G (MD manual maint)
Toledo scale | NO* | PnS | G (flat file to Dynasys ready) | G |  |  | G (TD) | N/A
* No data is sent, just retrieved from Satellite
** Stand alone systems have data being inputed manually

## Slide 4: PnS Satellite Systems Landscapes

## Slide 5: DYNASYS / Toledo Scale Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
Dynasys PROD (2003 server)
Before Go-live
Dynasys
IST / UAT (2008 server)
Dynasys PROD (2008 server)
After Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover steps:
Move ECC TRs
Business Cut off
Implement Changes in Dynasys PROD
Manually create MD in Dynasys PROD
Run Smoke test
(1)
(3);
(4);
(5)
RFC
zTCD
zTCD
zTCD
zTCD
TOLEDO scale
Before Go-live
TOLEDO scale
After Go-live
(2)
Alterado
TR

## Slide 6: TMS Kewill Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
POD
POI
POU
POP
TMS PROD
Before Go-live
TMS Sandbox
TMS PROD
After Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover Steps:
Move ECC TRs
Business Cut off
Move PI/PO TRs
Connect TMS PROD to POP
Manually create MD in TMS
Run Smoke test
(1)
(3)
(2)
(4)
(5); (6)
TMS Sandbox
Inbound: WebS
Outbound: IDOC
Inbound: WebS
Outbound: IDOC
Inbound: WebS
Outbound: IDOC
IDOC
IDOC
WS
WS

## Slide 7: GKO Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
POD
POI
POU
POP
GKO PROD
Before Go-live
GKO
GKO PROD
After Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover Steps:
Move ECC TRs
Business Cut off
Implement Changes in GKO
Move PI/PO TRs
Connect POP to FEP
Automatically create MD in GKO
Run Smoke test
(1)
(4)
(5)
(3); (6); (7)
GKO
ABAP Proxy
POD
POI
POU
POP
(2)
ABAP Proxy
ABAP Proxy
ABAP Proxy
CARRIERS
FTP
CARRIERS
FTP
SEFAZ
SEFAZ
JDBC
JDBC
JDBC
JDBC
WS
WS

## Slide 8: OneSource Global Trade Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
POD
POI
POU
POP
OSGT Dev
OSGT Prod
Cutover Steps:
Move ECC TRs
Move PI/PO TRs
Implement Changes in OSGT
Connect OSGT to POP
Automatically create MD in OSGT
Implement Changes in Configuration tables for OSGT
Run Smoke test
(1)
(2)
(4)
(3); (5); (7)
IDOC
IDOC
WS
WS
OSGT IST
OSGT UAT
WS
WS
(6)

## Slide 9: Carrier WebServices Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
POD
POI
POU
POP
Carrier WS Before Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover Steps:
Move ECC TRs
Move PI/PO TRs
Business Cut off
Decommision Carrier WS
Map Carrier http and FTP links
Run Smoke test
(1)
(2)
(3)
(5)
(6)
Carrier WS Support
IDOC
IDOC
WS and FTP
CARRIERS
CARRIERS
(4)
WS and FTP
Alterado
TR

## Slide 10: FiP Satellite Systems Landscapes

## Slide 11: HR (GPS) Satellite Landscape
TO-BE
AS-IS
GPS
Before Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover steps:
Business Cut Off
Move ECC TRs
Move HR TRs
Connect GPS to FEP
Run Smoke test
IDOC
GPT
Before Go-live
GPD
Before Go-live
(1)
IDOC
IDOC
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
(2)
(4);(5)
IDOC
IDOC
IDOC
IDOC
GPS
After Go-live
GPT
After Go-live
GPD
After Go-live
(3)

## Slide 12: Rhadar / Synseg Satellite Landscape
TO-BE
AS-IS
GPS
Before Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover steps:
GPS Cutover
Run Smoke test
GPT
Before Go-live
GPD
Before Go-live
Rhadar
Before Go-live
SynSEG
Before Go-live
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
IDOC
IDOC
IDOC
zTCD
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
IDOC
IDOC
IDOC
IDOC
GPS
After Go-live
GPT
After Go-live
GPD
After Go-live
(2)
Rhadar
After Go-live
SynSEG
After Go-live
(1)
zTCD

## Slide 13: GRC NFE Satellite Landscape
TO-BE
AS-IS
FFU
EhP7 SP12
FEP
EhP7 SP12
POD
POI
POU
POP
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover Steps:
Business Cut Off
Move ECC TRs
Move GRCNFE TRs
Move PI/PO TRs
Run Smoke test
(2)
(4)
LND
POD
POI
POU
POP
(1)
LNI
LNU
LNP
GND
GNI
GNU
LNP
(5)
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
RFC
RFC
RFC
RFC
ABAP Proxy
ABAP Proxy
ABAP Proxy
SEFAZ
WS
FFD
EhP7 SP12
FFT
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
RFC
RFC
RFC
RFC
ABAP Proxy
ABAP Proxy
ABAP Proxy
SEFAZ
WS
(3)

## Slide 14: MasterSAF DW Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
MSAF PRD
Cutover steps:
Business Cut Off
Move ECC TRs
Move MSAF AOL changes
Connect MSAF AOL to FEP
Run Smoke test
(2)
(4);(5)
MSAF QAS
MSAF DEV
MSAF AOL PRD
MSAF AOL QAS
MSAF AOL DEV
(1)
(1)
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
MSAF PRD
MSAF QAS
MSAF DEV
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(3)
(1)
Alterado
TR

## Slide 15: SERASA Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
POD
POI
POU
POP
Cutover Steps:
Move ECC TRs
Move PI/PO TRs
Map SERASA http links
Run Smoke test
(1)
(2)
(3)
(4)
IDOC
IDOC
WS?
SERASA
Review

## Slide 16: Credito Rural Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
Crédito Rural before Go-live
Crédito Rural IST/UAT
Crédito Rural after Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(1)
(3);
(4);
(5)
zTCD
zTCD
zTCD
zTCD
Cutover steps:
Move ECC TRs
Business Cut Off
Implement Changes in Credito Rural
Manually create MD in Credito Rural
Run Smoke test
Bank
zTCD
(2)
Bank

## Slide 17: Easy IRPJ Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
Easy IRPJ before Go-live
Easy IRPJ Support
Easy IRPJ after Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(1)
(3);
(4);
(5)
zTCD
zTCD
zTCD
zTCD
Cutover steps:
Move ECC TRs
Business Cut Off
Implement Changes in Easy IRPJ
Manually create MD in Easy IRPJ
Run Smoke test
zTCD
(2)
Easy IRPJ Support
Alterado
TR
zTCD

## Slide 18: VIM Satellite Landscape
TO-BE
AS-IS
FFU
EhP7 SP12
FEP
EhP7 SP12
POD
POI
POU
POP
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover Steps:
Business Cut Off
Move ECC TRs
Move GRCNFE TRs
Move PI/PO TRs
Run Smoke test
(2)
(4)
LND
POD
POI
POU
POP
(1)
LNI
LNU
LNP
GND
GNI
GNU
LNP
(5)
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
RFC
RFC
RFC
RFC
ABAP Proxy
ABAP Proxy
ABAP Proxy
SEFAZ
WS
FFD
EhP7 SP12
FFT
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
RFC
RFC
RFC
RFC
ABAP Proxy
ABAP Proxy
ABAP Proxy
SEFAZ
WS
(3)
Review

## Slide 19: Biller Direct Solution Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
POD
POI
POU
POP
OSGT Dev
OSGT Prod
Cutover Steps:
Move ECC TRs
Move PI/PO TRs
Implement Changes in OSGT
Connect OSGT to POP
Automatically create MD in OSGT
Implement Changes in Configuration tables for OSGT
Run Smoke test
(1)
(2)
(4)
(3); (5); (7)
IDOC
IDOC
WS
WS
OSGT IST
OSGT UAT
WS
WS
(6)
Review

## Slide 20: Integração Nutrace (Feedback – FeedSystem)
TO-BE
AS-IS
Alterado
TR

## Slide 21: PecSYN Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
PecSYN
VPM PROD Before Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(1)
(3);
(4);
(5)
zTCD
Cutover steps:
Move ECC TRs
Business Cut Off
Implement Changes in PecSYN PROD
Manually create MD in PecSYN PROD
Run Smoke test
EBI
zTCD
Review
Pricing SPoT
PecSYN
CMT PROD Before Go-live
PecSYN
SIP PROD Before Go-live
Extrapratica
SPBF
EBI
Pricing SPoT
PecSYN
CMT PROD After Go-live
PecSYN
SIP PROD After Go-live
PecSYN
VPM PROD After Go-live
(3);
(4);
(5)
(3);
(4);
(5)
(2)
(2)
(2)

## Slide 22
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
Plusoft
before Go-live
Plusoft Support
Plusoft
after Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(1)
(3);
(4);
(5)
zTCD
zTCD
zTCD
zTCD
Cutover steps:
Move ECC TRs
Business Cut Off
Implement Changes in Plusoft
Manually create MD in Plusoft
Run Smoke test
zTCD
(2)
Plusoft Support
Alterado
TR
zTCD
Plussoft Satellite Landscape
Review (in design)

## Slide 23
TO-BE
AS-IS
SPoT
before Go-live
SPoT
IST/UAT
SPoT
after Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(2)
(3);
Cutover steps:
Business Cut Off
Implement Changes in SPoT
Run Smoke test
zTCD
(1)
SPoT
Support
Alterado
TR
zTCD
SPoT Satellite Landscape
Review (in design)
Vendavo
Vendavo
IST/UAT

## Slide 24
TO-BE
AS-IS
Teamspace
before Go-live
Teamspace
after Go-live
(2)
(3);
Cutover steps:
Business Cut Off
Implement Changes in SPoT
Run Smoke test
Alterado
TR
Teamspace Satellite Landscape
Review (in design)
Teamspace
IST/UAT
(1)